## Plan Summary
Llavero - Secure Credentials & IT Asset System
v1 Build Plan & Day-to-Day Tracker
Record, report, and query only. Fully in-house, zero cost. Django + PostgreSQL + HTMX. Two admins, one viewer.
Source of truth: 00-Master-Index-and-Decision-Registry.md (D-01..D-33 locked). Detail in Annexes A-I.
Progress
Total tasks | 70
Done | 1
In progress | 2
Blocked | 0
Not started | 67
The eight phases (build security-first, fan out after the spine is proven)
Phase | Focus | Depends on | Size
0 | Confirm open points; provision hardened infrastructure | none | M
1 | Schema + security spine (encryption, audit, auth) via a thin vertical slice | 0 | L (long pole)
2 | Backups operational, before any real data | 1 | S-M
3 | Inventory CRUD, relationships, states, custom fields, UI | 1 | M-L
4 | Secrets: store, reveal, rotate, masking, recovery validated | 1, 3 | M
5 | Read-only integrations (Graph MFA, network gear) | 3 | M
6 | Alert engine (13 rules) and dashboard | 3, 4, 5 | M
7 | Release gate: full DR drill, security review, go-live | all | S-M
HARD RULE: do not load real secrets until backups run (P2-T6) and the recovery-key restore has passed (P4-T6). See Risks R-4.

## Milestones
Phase | Milestone | Goal | Definition of done | Depends on | Size
Phase 0 | Foundations | Confirm the open points (P-13/14/15) and stand up hardened infrastructure so the build starts on safe ground. | P-13/14/15 confirmed and recorded in the registry; server provisioned per Annex G (minimal OS, LUKS2 TPM+PIN, default-deny firewall, VPN-only path, restricted egress); separate anchoring/log/backup host confirmed or provisioned; no app code or real data yet. | none | M
Phase 1 | Schema + security spine | Stand up the Django project and the Annex C schema, then build encryption, audit log, and auth, proven end to end through a thin vertical slice before fanning out. | Thin slice (one entity, one secret, one logged change, one login) works end to end; chain verifies; master key never on disk or swap; Viewer session holds no key; per-admin wrapping works; printed recovery key generated and in the safe. | Phase 0 | L (long pole)
Phase 2 | Backups operational | Daily encrypted dumps to three destinations and a first restore dry run, before any real data exists. | Daily encrypted pg_dump on a timer; three copies including the offsite office; backup public key on server, private key offline in the safe; first restore dry run passes including chain verify and a recovery-key decrypt. No WAL in v1 (P-15). | Phase 1 | S-M
Phase 3 | Inventory | Full CRUD for people, accounts, devices, offices, the nine join tables, states, custom fields, and a responsive HTMX UI. Writes audited, reads logged. | Every entity type recordable and relatable quickly from any entity page; states enforced (no hard deletes); custom fields render typed and honor viewer_visible; writes produce audit entries; reads produce record_view/list_view/search per granularity; Viewer masking holds server-side. | Phase 1 | M-L
Phase 4 | Secrets | Reveal with per-action reauth, rotation, keyless Viewer masking, and a validated recovery-key path. Encryption meets the UI. | Admin reveals with step-up and a logged reason, transient display + clipboard auto-clear; rotation works; Viewer masked and keyless; create/rotate/reveal logged; recovery-key reveal path validated (pairs with Phase 2 to clear the real-secrets gate). | Phases 1, 3 | M
Phase 5 | Integrations (read-only) | Graph MFA pull plus network monitoring (WatchGuard, MikroTik, UniFi), telemetry kept off the audit chain. | Daily Graph pull updates mfa_state/mfa_types via certificate auth and read-only scopes (no write scopes requested); gear polled every 5 min into network_device_detail + telemetry; only meaningful transitions chained; integration secrets in the vault; egress restricted to Graph + gear. | Phase 3 | M
Phase 6 | Alerts + dashboard | The 13 rules, dashboard grouping and acknowledge flow, and the integrity strip. Needs real-ish data and the integrations to be meaningful. | Scheduled (15 min) + on-demand evaluation by a system actor; alert table open/acknowledged/resolved with auto-resolve (rotation-evidence exceptions); 13 rules including E-1 (phones+tablets+laptops); thresholds in the setting table; integrity strip shows chain status; E-13 self-monitors. | Phases 3, 4, 5 | M
Phase 7 | Release gate | Full DR drill through the recovery-key path, a security pass over egress and roles, handover polish, then load real data and go live. | Full DR drill on new/isolated hardware passes via the recovery-key path and the chain verifies against off-box checkpoints; security pass clean (egress, role/field matrix, Viewer export block, single session); handover countdown polished; real data loaded only after the gate; v1 definition-of-done checklist signed off. | all | S-M

## Tasks
Task breakdown - each task cites the annex/section it implements and its dependencies. [GATE] and [VERIFY] rows are checkpoints.
Task ID | Phase | Task | Implements (annex / section) | Depends on | Gate / reauth | Status | Owner | Notes
P0-T1 | Phase 0 | Confirm P-13: alert thresholds + E-1 unrecoverable device scope | Annex E 5, 9; Annex F 9 | - | Confirmation | Done |  | E-1 set to phones+tablets+laptops; other thresholds keep Annex E 5 defaults, tunable in the setting table
P0-T2 | Phase 0 | Confirm P-14: TPM presence, separate host, disk unlock mode | Annex G 10 (3,4,7) | - | Confirmation | In progress |  | TPM 2.0 present -> TPM sealing + TPM/PIN. Separate host = decide in Phase 0 (P0-T9)
P0-T3 | Phase 0 | Confirm P-15: RPO target, offsite office, drill cadence | Annex H 11 (3,4,9) | - | Confirmation | In progress |  | RPO = daily dumps (no WAL); drill quarterly. OFFSITE OFFICE STILL TO SPECIFY
P0-T4 | Phase 0 | Record confirmations in the decision registry | Master Index 3, 6 | P0-T1, P0-T2, P0-T3 |  | Not started |  | Keep no decision trapped in chat
P0-T5 | Phase 0 | Provision minimal hardened OS (Ubuntu 24.04, AppArmor/SELinux, chrony, swap off/encrypted, core dumps off) | Annex G 2 | P0-T2 |  | Not started
P0-T6 | Phase 0 | LUKS2 full-disk encryption, unlock bound to TPM2 + PIN | Annex G 3 | P0-T2, P0-T5 |  | Not started |  | Boot passphrase is the stricter alternative if reboots are attended
P0-T7 | Phase 0 | Default-deny firewall (nftables/ufw) + SSH lockdown (key-only, no root) + fail2ban | Annex G 2, 8 | P0-T5 |  | Not started
P0-T8 | Phase 0 | Establish VPN-only access path (WatchGuard SSL VPN / MikroTik tunnels) with VPN MFA | Annex G 6 | P0-T7 |  | Not started |  | Outer of three auth layers
P0-T9 | Phase 0 | Provision/confirm the separate internal host (append-only checkpoints, shipped logs, backup copy 1) | Annex G 7; Annex H 4 | P0-T2 |  | Not started |  | Resolves the open part of P-14
P0-T10 | Phase 0 | Restrict outbound egress to Graph endpoints + LAN/tunnel reach only | Annex G 1, 8; Annex F 7 | P0-T7 |  | Not started
P1-T1 | Phase 1 | Scaffold Django + PostgreSQL (scram-sha-256, localhost bind, reverse proxy internal-CA TLS, hardened systemd unit) | Annex G 5; Prelim 8 | P0-T5 |  | Not started
P1-T2 | Phase 1 | Annex C core entity models (operator, person, account, device, network_device_detail, office, secret, field_definition): UUIDv4, base mixin, enums | Annex C 2, 3, 4, 9 | P1-T1 |  | Not started
P1-T3 | Phase 1 | Nine relationship join tables with FK integrity + partial unique indexes | Annex C 5, 6 | P1-T2 |  | Not started
P1-T4 | Phase 1 | Session tables (operator_session, session_request) | Annex C 4.3, 4.3b | P1-T2 |  | Not started
P1-T5 | Phase 1 | Argon2id calibration on the real server (~4s target, 1-2 GiB, parallelism = cores) | Annex A 5.1, 11 | P0-T5 |  | Not started |  | Store params next to the wrapped MK for future recalibration
P1-T6 | Phase 1 | Envelope encryption passphrase->KWK->MK->DEK, XChaCha20-Poly1305 + AAD (PyNaCl, argon2-cffi) | Annex A 3, 4, 11; Annex C 4.9 | P1-T5 |  | Not started
P1-T7 | Phase 1 | Vault second factor: TPM 2.0 sealing combined via HKDF (keyfile fallback) | Annex A 5.2; Annex G 4 | P1-T6, P0-T6 |  | Not started |  | Per P-14, TPM path confirmed
P1-T8 | Phase 1 | Master key in memory: mlock, memzero on lock/logout/shutdown, idle auto-lock, no core dumps (Model A) | Annex A 6, 7; Annex G 2 | P1-T6 |  | Not started |  | See risk R-2
P1-T9 | Phase 1 | Per-administrator key wrapping: vault_key_holder table, enroll/remove + MK rotation | Annex A 13 | P1-T6 |  | Not started |  | Two admins, one MK wrapped per admin
P1-T10 | Phase 1 | Generate printed recovery key + safe-storage procedure (independent MK wrap) | Annex A 8 | P1-T6 |  | Not started |  | DR linchpin, see risk R-6
P1-T11 | Phase 1 | Audit schema (audit_entry, audit_checkpoint) + append-only DB role + BEFORE UPDATE/DELETE trigger | Annex B 4, 5; Annex G 5 | P1-T2 |  | Not started
P1-T12 | Phase 1 | Hash chain: BLAKE2b-256, canonical length-prefixed payload, same-transaction insert, advisory-lock ordering | Annex B 3, 5 | P1-T11 |  | Not started |  | See risk R-3
P1-T13 | Phase 1 | Chain verification (walk + anchor check) + signed checkpoint via Admin WebAuthn signing | Annex B 7; Annex G 7 | P1-T12, P1-T9 |  | Not started
P1-T14 | Phase 1 | Off-box checkpoint anchoring to the separate host (append-only) + printed-copy procedure | Annex G 7; Annex B 2 | P1-T13, P0-T9 |  | Not started |  | Resists a malicious admin, see risk R-7
P1-T15 | Phase 1 | Operator auth: login password (Argon2id hash), WebAuthn (py_webauthn) + TOTP (pyotp) | Annex D 1, 2; Annex C 4.1, 4.2; Prelim 6 | P1-T1, P1-T2 |  | Not started |  | Login independent of M365/Entra
P1-T16 | Phase 1 | Single active session via advisory lock; Viewer session never unlocks the MK | Annex D 2, 8; Annex C 4.3 | P1-T4, P1-T15 |  | Not started |  | Keyless Viewer is a cryptographic fact, not just policy
P1-T17 | Phase 1 | Step-up reauth framework (per-action + windowed ~2 min) + idle auto-lock | Annex D 6 | P1-T15, P1-T8 | Reauth | Not started |  | Confirm window length (P7-T4)
P1-T18 | Phase 1 | Session handover hybrid B+C: idle-yield 120s, grace 300s, extend +600s, release-now, depleting-bar cue | Annex D 8 (chosen config); Annex C 4.3b | P1-T16 |  | Not started |  | Release-now locked first 5s; amber <60s, red <20s
P1-T19 | Phase 1 | Thin vertical slice: one entity + one secret + one logged change + one login, end to end | Annex I 3 (Phase 1) | P1-T6, P1-T12, P1-T15, P1-T16 |  | Not started |  | Flushes out the two riskiest areas early (R-1)
P1-T20 | Phase 1 | [VERIFY] Spine test pass: chain verifies; MK absent from disk/swap/core; Viewer cannot decrypt | Annex I 4, 5 | P1-T19 | [VERIFY] | Not started |  | Do not fan out until this passes
P2-T1 | Phase 2 | Daily pg_dump on a timer; asymmetric encrypt at rest (age/gpg), public key on server | Annex H 3 | P1-T2 |  | Not started |  | No WAL in v1 per P-15; revisit if RPO tightens
P2-T2 | Phase 2 | Three destinations: separate host (copy 1), second host/NAS (copy 2), offsite office over MikroTik tunnel (copy 3) | Annex H 4 | P2-T1, P0-T9 |  | Not started |  | 3-2-1, all copies encrypted; offsite office to specify
P2-T3 | Phase 2 | Keep private key / recovery key / keyfile in the safe, never with the backups | Annex H 5 | P2-T1 |  | Not started |  | See risk R-6
P2-T4 | Phase 2 | Retention GFS: daily 14d, weekly 8w, monthly 12m; chain never pruned | Annex H 6 | P2-T1 |  | Not started
P2-T5 | Phase 2 | Backup monitoring: success/failure logged + shipped to the separate host; seed backup_overdue alert | Annex H 10 | P2-T1, P1-T14 |  | Not started |  | Natural addition to the Annex E catalog
P2-T6 | Phase 2 | [GATE] First restore dry run to an isolated env: DB loads, chain verifies, a secret decrypts via the recovery-key path | Annex H 8, 9 | P2-T1, P2-T3, P1-T13 | [GATE] | Not started |  | NO REAL SECRETS until this passes (R-4)
P3-T1 | Phase 3 | CRUD + forms for person, account, device, office (+ network_device_detail) | Annex C 4; Prelim 3 | P1-T2 |  | Not started
P3-T2 | Phase 3 | Relationship UI: create/end typed links from any entity page (find, pick type, save) | Annex C 5; Prelim 4 | P1-T3, P3-T1 |  | Not started |  | Speed of relating is a core requirement
P3-T3 | Phase 3 | State machines per entity + no-hard-delete (terminal states only) | Annex C 1, 3 | P3-T1 |  | Not started |  | Preserves the audit chain
P3-T4 | Phase 3 | Custom fields: field_definition admin + typed rendering + viewer_visible | Annex C 4.10, 9; Annex D 5 | P3-T1 |  | Not started
P3-T5 | Phase 3 | Responsive HTMX UI + list/search | Prelim 8; Annex D 4 | P3-T1 |  | Not started
P3-T6 | Phase 3 | Wire writes to the audit chain + read-logging granularity (record_view/list_view/search; no pagination) | Annex B 6; Annex D 6 | P1-T12, P3-T1 |  | Not started |  | Implements D-24 read logging
P3-T7 | Phase 3 | Field-level permissions + serializer masking; server-side action matrix | Annex D 3, 4, 5, 9 | P3-T1, P1-T17 |  | Not started |  | Server is the boundary, UI masking is presentation only
P3-T8 | Phase 3 | [VERIFY] Audit coverage check + Viewer masking holds server-side | Annex B 6; Annex D 9 | P3-T6, P3-T7 | [VERIFY] | Not started
P4-T1 | Phase 4 | Secret store UI: create a secret per kind, AAD bound to the record | Annex A 3, 10; Annex C 4.9; Annex D 4 | P1-T6, P3-T1 | Reauth | Not started
P4-T2 | Phase 4 | Reveal flow: step-up reauth (no cache) + reason, transient display, clipboard auto-clear, never logged/cached | Annex D 6, 7; Annex A 6 | P1-T8, P1-T17, P4-T1 | Reauth | Not started
P4-T3 | Phase 4 | Rotation: new DEK + ciphertext, last_rotated_at; secret_rotate logged | Annex A 9; Annex C 4.9 | P4-T1 | Reauth | Not started
P4-T4 | Phase 4 | Viewer masking backed by the keyless session (cryptographic, not just policy) | Annex D 2, 5 | P1-T16 |  | Not started
P4-T5 | Phase 4 | Secret audit coverage (create/rotate/reveal/state_change, non-sensitive facts only) | Annex B 6 | P1-T12, P4-T1 |  | Not started |  | Never the plaintext, never full ciphertext
P4-T6 | Phase 4 | [GATE] Recovery-key reveal path validated end to end | Annex A 8; Annex H 7, 9 | P4-T2, P2-T6 | [GATE] | Not started |  | Pairs with P2-T6 to release real secrets (R-4)
P5-T1 | Phase 5 | integration table + scheduler (per-interval runs, last_run_at/last_status) | Annex F 2 | P3-T1 |  | Not started
P5-T2 | Phase 5 | Graph app registration (app-only, certificate auth), read-only scopes (User.Read.All + AuditLog.Read.All / UserAuthenticationMethod.Read.All); cert as a secret | Annex F 3; Annex G 6 | P5-T1, P4-T1 |  | Not started |  | No write scopes requested at all (R-5)
P5-T3 | Phase 5 | Graph MFA pull daily: userRegistrationDetails -> account.mfa_state/mfa_types; match by external_id; surface unmatched | Annex F 3, 8 | P5-T2 |  | Not started |  | Idempotent, never deletes
P5-T4 | Phase 5 | Network monitoring: WatchGuard SNMPv3, MikroTik RouterOS API/TLS or SNMP, UniFi controller API/HTTPS; creds as secrets; 5-min cadence | Annex F 4, 7 | P5-T1, P4-T1 |  | Not started |  | 5-min cadence makes E-9 offline = 3 missed polls
P5-T5 | Phase 5 | Telemetry table + transition-only chaining; live network_device_detail update | Annex F 6; Annex B 5 | P5-T4, P1-T12 |  | Not started |  | Raw telemetry stays off the audit chain
P5-T6 | Phase 5 | [VERIFY] Read-only proof: no write scopes, egress limited to Graph + gear, telemetry off-chain | Annex F 1, 7; Annex I 5 | P5-T3, P5-T5 | [VERIFY] | Not started
P6-T1 | Phase 6 | alert + setting tables; idempotent eval keyed by (rule_id, target); system actor reads not logged | Annex E 3, 4 | P3-T1 |  | Not started
P6-T2 | Phase 6 | Scheduled evaluator (eval_interval default 15) + on-demand dashboard refresh | Annex E 3 | P6-T1 |  | Not started
P6-T3 | Phase 6 | Implement the 13 rules E-1..E-13 over the relationship graph | Annex E 6; Annex C 7 | P6-T1, P3-T2, P5-T5 |  | Not started |  | E-1 scope = phones+tablets+laptops (P-13). E-1 reads account_device_config (Annex C); fix Annex E wording 'account_configured_on_device'
P6-T4 | Phase 6 | Auto-resolve + rotation-evidence exceptions (account_compromised, needs_rotation) | Annex E 3, 6 | P6-T3, P4-T3 |  | Not started
P6-T5 | Phase 6 | Dashboard: severity grouping, acknowledge w/ note (Admin), filters, entity links | Annex E 7; Annex D 4 | P6-T3 |  | Not started |  | Viewer sees all, cannot acknowledge
P6-T6 | Phase 6 | Integrity strip + E-13 self-monitoring ('verified through seq N, last checkpoint at T') | Annex E 7, 8; Annex B 7 | P6-T3, P1-T13 |  | Not started |  | Makes the audit log watch itself
P6-T7 | Phase 6 | Thresholds in the setting table, Admin-editable + parameter_change logged | Annex E 5; Annex D 4 | P6-T1 | Reauth | Not started |  | Defaults per P-13
P6-T8 | Phase 6 | [VERIFY] Rule-firing tests incl. E-1 on seeded data; alert state changes logged, eval reads not | Annex E 8; Annex I 4 | P6-T3, P5-T5 | [VERIFY] | Not started
P7-T1 | Phase 7 | [GATE] Full DR drill to new hardware: provision, restore offsite backup, unlock via recovery key, re-seal TPM, re-enroll admins, re-point integrations, verify chain | Annex H 7, 8; Annex G 9 | P2-T6, P4-T6 | [GATE] | Not started |  | The recovery key is the single linchpin (R-6)
P7-T2 | Phase 7 | Security pass: egress, role/field matrix, Viewer export block, single session | Annex D 4, 9; Annex F 7; Annex G 1, 8; Annex I 5 | P3-T8, P4-T6, P5-T6, P6-T8 |  | Not started
P7-T3 | Phase 7 | Handover polish + countdown QA (amber <60s, red <20s, release locked first 5s) | Annex D 8 | P1-T18 |  | Not started
P7-T4 | Phase 7 | Confirm reauth window (2 min default) + idle auto-lock alignment | Annex D 6, 10 | P1-T17 | Confirmation | Not started |  | Annex D open point 4/5
P7-T5 | Phase 7 | [GATE] Load real data + go live | Annex I 3 (Phase 7), 4 | P7-T1, P7-T2 | [GATE] | Not started |  | Only after the DR drill + recovery-key path pass (R-4)
P7-T6 | Phase 7 | [VERIFY] v1 definition-of-done checklist signed off | Annex I 4 | P7-T1, P7-T2, P7-T3, P7-T5 | [VERIFY] | Not started

## Risks
ID | Risk | Source | Severity | Mitigation | Phase(s)
R-1 | Phase 1 is the long pole and the riskiest part of the build | Annex I 5 | High | Build the thin vertical slice first to flush out spine issues early; do not fan out until P1-T20 passes | 1
R-2 | Master key exposed by a memory dump while a session is open (Model A) | Annex A 6; Annex I 5 | High | mlock + memzero on lock/logout/shutdown, idle auto-lock, swap off/encrypted, core dumps disabled | 1
R-3 | Audit chain ordering breaks under concurrent monitoring writes | Annex B 5; Annex I 5 | High | Advisory-lock serialization, same-transaction insert, gap-free seq; prove it in the slice | 1
R-4 | Real secrets loaded before backup + recovery are proven (data could be unrecoverable) | Annex I 5; project rule | Critical | HARD GATE: no real secrets until P2-T6 restore dry run AND P4-T6 recovery-key path both pass; final release at P7-T5 | 2,4,7
R-5 | Integration scope creep from read-only to writing M365 or the gear | Annex I 5; Annex F 1 | High | Request read-only scopes only, no write permissions, egress firewalled; hold the line in v1 | 5
R-6 | Lockout: the printed recovery key is the single DR linchpin | Annex A 8; Annex G 9; Annex H 7 | Critical | Printed recovery key in the safe, tested before go-live + quarterly; private key/keyfile in the safe, never with backups | 0,2,7
R-7 | Malicious-admin tampering: a hash chain alone is detection-only | Annex B 2 | Medium-High | Signed off-box checkpoints via Admin WebAuthn signing + printed copies on an append-only host | 1,7
R-8 | TPM hardware binding could block unlock on server failure | Annex G 4, 9 | Medium | Recovery-key path to new hardware + re-seal to the new TPM; keyfile fallback documented | 2,7

## Confirmations P13-14-15
ID | Topic | Decision / value | Default was | Status | Source
P-13 | Alert thresholds + E-1 unrecoverable device scope | E-1 covers phones, tablets, and laptops; other thresholds keep Annex E 5 defaults (tunable in setting table) | phones only | Confirmed (your choice) | Annex E 5, 9; Annex F 9
P-14a | TPM 2.0 presence -> vault second factor + disk unlock | TPM 2.0 present: TPM sealing as the vault factor, TPM + PIN for LUKS2 | TPM + PIN | Confirmed | Annex G 3, 4
P-14b | Separate anchoring / log / backup host | Decide in Phase 0; provision a small one if none exists | provision if absent | Open (Phase 0, P0-T9) | Annex G 7; Annex H 4
P-14c | Disk unlock mode | TPM + PIN (follows from TPM present) | TPM + PIN | Confirmed (default) | Annex G 3
P-15a | RPO target | Daily encrypted dumps, 24h RPO. No WAL archiving in v1 | daily | Confirmed | Annex H 3, 11
P-15b | Offsite office (replication target) | To specify which office is the tunnel target | - | Open (Phase 0, P0-T3) | Annex H 4, 11
P-15c | Drill cadence | Quarterly restore drill including the recovery-key path | quarterly | Confirmed (default) | Annex H 9, 11
(D-side) | Reauth window + idle auto-lock alignment | 2 min windowed reauth is a starting value; confirm and align idle auto-lock | 2 min | Open (confirm, P7-T4) | Annex D 6, 10

## Decisions (D-01..D-33)
Locked decisions, from Master Index section 3. Reference only - treat as settled.
ID | Topic | Decision
D-01 | Build approach | 100% in-house, a single application
D-02 | Cost | Zero. Free software only, no paid services or third parties
D-03 | v1 scope | Record, report, and query only. No advanced operations
D-04 | Secret storage | Encrypted field inside the same PostgreSQL. No external vault
D-05 | Data encryption | XChaCha20-Poly1305, 256-bit, AAD bound to the record
D-06 | Key derivation | Argon2id, 1-2 GiB, calibrated to ~4s on the real server
D-07 | Key hierarchy | Envelope encryption: passphrase -> KWK -> MK -> per-secret DEK
D-08 | Second factor (partial) | Key material outside the DB. WebAuthn PRF a future premium
D-09 | Key in memory | Model A: derive at unlock, MK in locked memory, idle auto-lock
D-10 | Stack | Django, PostgreSQL, HTMX, PyNaCl, argon2-cffi, pyotp, py_webauthn
D-11 | Roles and session | Administrator and Viewer roles. One active session at a time
D-12 | Login MFA | Platform WebAuthn first, TOTP alternative. Hardware keys future
D-13 | Integrations | All read only. M365 Graph for users + MFA. Odoo/ZKBioTime deferred
D-14 | Hosting and access | Local server, no internet exposure, remote via VPN only
D-15 | Audit log (concept) | Append-only, hash chained, with who/when/what
D-16 | Backup (concept) | Encrypted pg_dump, own + offsite copy, tested restore
D-17 | Anti-lockout recovery | Printed recovery key in a safe, keyfile backup, Shamir optional
D-18 | Plan format/language | Modular markdown files, English
D-19 | Primary keys | UUID v4 for every table
D-20 | Relationship modeling | Explicit join tables with DB-enforced integrity
D-21 | Multi-owner accounts | Supported in v1 via account_ownership (primary or shared)
D-22 | v1 scope trims | Per-NIC detail, richer network detail, IPAM deferred to v2
D-23 | Audit log design | Append-only role+trigger, BLAKE2b-256 chain, same-tx writes, advisory lock, signed external checkpoints
D-24 | Read logging | Reads logged into the chain (record_view, list_view, search). Monitoring reads excluded
D-25 | Permissions model | Two roles. Viewer session never holds the MK. Step-up reauth. Single session
D-26 | Administrators | Two admins. One MK wrapped per admin (multi-recipient). Enroll/remove defined
D-27 | Viewer exports | Viewer fully blocked from exports
D-28 | Session handover | Hybrid B/C. Idle yield 120s, grace 300s, extend +600s, release now. Depleting bar
D-29 | Alert engine | 13 rules, three severities, scheduled + on-demand, alert table, thresholds in setting
D-30 | Integrations detail | Graph app-only cert read-only daily; gear via SNMPv3/scoped APIs every 5 min
D-31 | Hardening/deployment | One internal server, no exposure, VPN+MFA, LUKS2 TPM+PIN, TPM-sealed vault factor, signed checkpoints off-box
D-32 | Backup and recovery | Daily encrypted pg_dump (optional WAL), asymmetric, 3 copies incl offsite. Recovery key is the linchpin
D-33 | MVP scope and phases | v1 record/report/query. Eight phases, security spine first via thin slice